## AI Register
AI Use-Case Register
Enter one row for each material AI application. The Dashboard summarises this sheet automatically.
Use Case ID | AI Application / Use Case | Business Area | Business Owner | Risk Rating | Status | Registered? | Risk Assessed? | Human Oversight? | Vendor Assessed? | Last Review | Next Review | Annual Benefit | Hours Released YTD
AI-001 | Customer Service Assistant | Customer Service | Customer Services Director | Medium | Live | Yes | Yes | Yes | Yes | 2026-07-01 | 2026-10-01 | 180000 | 5200
AI-002 | Recruitment Screening | HR | HR Director | High | Pilot | Yes | Yes | Yes | Yes | 2026-07-15 | 2026-08-31 | 40000 | 500
AI-003 | Financial Forecasting AI | Finance | CFO | High | Live | Yes | Yes | Yes | Yes | 2026-07-10 | 2026-10-10 | 260000 | 2300
AI-004 | Enterprise Copilot | Enterprise | CIO | Low | Live | Yes | Yes | Yes | Yes | 2026-06-30 | 2027-06-30 | 420000 | 6100
AI-005 | Knowledge Assistant | Operations | COO | Medium | Pilot | Yes | No | Yes | Yes | 2026-07-20 | 2026-09-20 | 120000 | 1800
AI-006 | Contract Review Assistant | Legal | General Counsel | Medium | Live | Yes | Yes | Yes | No | 2026-07-25 | 2027-01-25 | 90000 | 1500
AI-007 | Marketing Content Assistant | Marketing | CMO | Low | Live | No | No | Yes | Yes | 2026-07-28 | 2027-07-28 | 70000 | 1000

## People & Training
People & Training
Enter workforce adoption and training figures by business area.
Business Area | Eligible Employees | AI Training Completed | Active Approved AI Users | AI Champions
Customer Service | 180 | 160 | 145 | 3
Finance | 85 | 78 | 61 | 2
HR | 55 | 47 | 32 | 1
Operations | 140 | 115 | 92 | 3
Marketing | 45 | 40 | 36 | 1
Legal | 35 | 29 | 22 | 2

## Incidents
AI Incidents & Issues
Record AI-related incidents, issues and material governance exceptions.
Incident ID | Date | AI Application / Use Case | Severity | Status | Description | Business Owner | Executive Attention?
INC-001 | 2026-07-05 | Customer Service Assistant | Low | Closed | Incorrect customer response identified during employee review. | Customer Services Director | No
INC-002 | 2026-07-19 | Enterprise Copilot | Medium | Closed | Sensitive information pasted into an unapproved prompt workflow. | CIO | No
INC-003 | 2026-08-02 | Recruitment Screening | Medium | Open | Bias monitoring threshold exceeded during pilot testing. | HR Director | Yes

## Actions
Governance Actions
Track management actions and Board decisions arising from AI governance.
Action ID | Action / Decision | Owner | Due Date | Priority | Status | Board Decision Required? | Notes
ACT-001 | Complete enhanced review of Recruitment Screening pilot | HR Director | 2026-08-31 | High | In Progress | No | Bias and human oversight review before production approval.
ACT-002 | Complete controls for unapproved external AI services | CIO | 2026-09-15 | High | In Progress | No | Restrict access and reinforce employee guidance.
ACT-003 | Increase AI governance training completion to 90% | HR Director | 2026-09-30 | Medium | Not Started | No | Target all eligible employees.

## KPI Targets
Governance KPI Targets
Adjust targets and weights to match your organisation's governance appetite. Weights should total 100%.
KPI | Target | Weight | Notes
AI systems registered | 100% | 15% | Share of active AI use cases recorded in the register.
Risk assessments completed | 100% | 15% | Share of active use cases with a completed risk assessment.
Named business owners | 100% | 15% | Share of active use cases with a named owner.
High/Critical with human oversight | 100% | 15% | Share of high/critical use cases with human oversight.
Governance reviews current | 95% | 10% | Share of active use cases whose next review is not overdue.
Approved vendors assessed | 100% | 10% | Share of active use cases with vendor assessment completed.
AI training completed | 90% | 15% | Share of eligible employees who completed AI training.
No critical open incidents | 100% | 5% | 1 if there are no open critical incidents, otherwise 0.

## Dashboard
EXECUTIVE AI GOVERNANCE DASHBOARD
Example dashboard – replace sample source data on the supporting tabs with your organisation's figures.
Reporting Date | 2026-08-09 |  | Overall Governance Status | AMBER — IMPROVEMENT REQUIRED |  | Governance Score | 81.62%
AI ESTATE |  |  | HIGH / CRITICAL RISK |  |  | TRAINING COMPLETE |  |  | OPEN INCIDENTS
7 |  |  | 2 |  |  | 86.85% |  |  | 1
AI RISK PROFILE | [5 empty] | BUSINESS VALUE & ADOPTION
Risk | Count |  | Risk | Interpretation | Executive View | Measure | Current | Comment
Low | 2 |  | Low | Routine productivity / low consequence | Standard controls | Annualised Benefit | 1180000 | Estimated benefit recorded in AI Register
Medium | 3 |  | Medium | Business process / organisational data | Owner + assessment | Hours Released YTD | 18400 | Capacity released; not necessarily cash savings
High | 2 |  | High | Material decisions / sensitive data | Enhanced oversight | Active Approved AI Users | 388 | Across all business areas
Critical | 0 |  | Critical | Potential major rights/safety/financial impact | Executive assurance | AI Champions | 12 | Across all business areas
EXECUTIVE ACTIONS / DECISIONS
Action | Owner | Due | Priority | Status | Board Decision?
Complete Recruitment Screening review | HR Director | 31-Aug-2026 | High | In Progress | No
Control unapproved external AI services | CIO | 15-Sep-2026 | High | In Progress | No
Raise AI governance training to 90% | HR Director | 30-Sep-2026 | Medium | Not Started | No
GOVERNANCE CONTROL SCORECARD
KPI | Current | Target | Weight | Target Achievement
AI systems registered | 85.71% | 100% | 15% | 85.71%
Risk assessments completed | 71.43% | 100% | 15% | 71.43%
Named business owners | 100% | 100% | 15% | 100%
High/Critical with human oversight | 100% | 100% | 15% | 100%
Governance reviews current | 0% | 95% | 10% | 0%
Approved vendors assessed | 85.71% | 100% | 10% | 85.71%
AI training completed | 86.85% | 90% | 15% | 96.5%
No critical open incidents | 100% | 100% | 5% | 100%