## Project Approval Checklist
AI PROJECT APPROVAL CHECKLIST
Executive governance gate for approving AI projects before pilot and production.
Project / Use Case | [Enter name] | AI Use-Case ID | [Enter ID]
Business Owner | [Enter owner] | Executive Sponsor | [Enter sponsor]
Project Stage | [Enter stage] | Risk Classification | [Low / Moderate / High / Critical]
Approval Meeting Date | [Enter date] | Approval Body | [Enter authority]
ID | Approval Domain | Approval Check | Evidence Required | Response | Mandatory? | Owner | Required Action / Condition | Evidence / Reference | Gate Result
AP01 | Business Case | Is the business problem, opportunity and intended outcome clearly defined? | Problem statement and intended outcome. |  | Yes | Business Owner |  |  | Pending
AP02 | Business Case | Are measurable success criteria and KPIs defined? | Baseline, targets and benefits owner. |  | Yes | Business Owner |  |  | Pending
AP03 | Business Case | Is expected value proportionate to cost, complexity and risk? | Business case / ROI estimate. |  | No | Sponsor |  |  | Pending
AP04 | Ownership & Accountability | Is there a named business owner accountable for the AI outcome? | Named accountable owner. |  | Yes | Sponsor |  |  | Pending
AP05 | Ownership & Accountability | Are executive sponsorship and decision rights clear? | Sponsor and approval authority. |  | Yes | Sponsor |  |  | Pending
AP06 | Use-Case Governance | Is the project recorded in the AI Use-Case Register? | AI Use-Case ID / register entry. |  | Yes | AI Governance |  |  | Pending
AP07 | Use-Case Governance | Has the AI Risk Classification Matrix been completed? | Recorded classification. |  | Yes | AI Governance |  |  | Pending
AP08 | Risk Assessment | Has a detailed AI Risk Assessment been completed where required? | Assessment and residual risks. |  | Yes | Risk Owner |  |  | Pending
AP09 | Risk Assessment | Are High/Critical residual risks explicitly accepted or reduced? | Risk treatment / authorised acceptance. |  | Yes | Risk Owner |  |  | Pending
AP10 | Data & Privacy | Is the proposed data appropriate for the approved AI environment? | Data classification / permitted use. |  | Yes | Data / Privacy |  |  | Pending
AP11 | Data & Privacy | Have privacy, retention, deletion and data-location requirements been addressed? | Privacy review / DPIA where applicable. |  | Yes | Privacy |  |  | Pending
AP12 | Security | Are identity, access, least-privilege and credential controls defined? | Security/access design. |  | Yes | Security |  |  | Pending
AP13 | Security | Have prompt injection, malicious input and external-content risks been considered? | Threat assessment / mitigations. |  | No | Security |  |  | Pending
AP14 | Vendor / Third Party | Has the AI Vendor Assessment been completed for material external suppliers? | Vendor due diligence / conditions. |  | Yes | Procurement / Risk |  |  | Pending
AP15 | Legal & Compliance | Have legal, regulatory, contractual and IP issues been reviewed? | Legal/compliance review. |  | Yes | Legal / Compliance |  |  | Pending
AP16 | Human Oversight | Is the human review/approval/decision boundary explicitly defined? | Oversight design / escalation points. |  | Yes | Business Owner |  |  | Pending
AP17 | Human Oversight | Can authorised staff override, suspend or stop the AI-supported process? | Intervention mechanism. |  | Yes | Business / Technology |  |  | Pending
AP18 | Testing & Assurance | Has the system been tested for accuracy, reliability and expected failure modes? | Test results / acceptance criteria. |  | Yes | Project / QA |  |  | Pending
AP19 | Testing & Assurance | For higher-risk AI, has adversarial or misuse testing been completed where appropriate? | Safety/security test evidence. |  | No | Security / QA |  |  | Pending
AP20 | Agentic AI | If AI can take actions, are permissions, tools and systems explicitly allow-listed? | Agent permission design. |  | Yes | Technology / Security |  |  | Pending
AP21 | Agentic AI | Are transaction, volume, financial and time limits defined for autonomous activity? | Configured operating limits. |  | Yes | Business / Technology |  |  | Pending
AP22 | Agentic AI | Is there a reliable kill switch / disable mechanism for materially consequential autonomous AI? | Tested shutdown control. |  | Yes | Technology |  |  | Pending
AP23 | Monitoring | Are logging, performance monitoring and risk indicators defined? | Monitoring plan / metrics / alerts. |  | Yes | Technology / Risk |  |  | Pending
AP24 | Monitoring | Are review frequency and re-approval triggers defined? | Review schedule / change triggers. |  | Yes | AI Governance |  |  | Pending
AP25 | Incident Management | Is there an AI incident and escalation process for unexpected or unauthorised behaviour? | Incident process / contacts. |  | Yes | Risk / Security |  |  | Pending
AP26 | Change Management | Will material model, vendor, data, permission or autonomy changes trigger reassessment? | Change-control requirements. |  | Yes | Project Owner |  |  | Pending
AP27 | People & Adoption | Have affected users received appropriate training and operating guidance? | Training / communications evidence. |  | No | Business Owner |  |  | Pending
AP28 | Production Readiness | Are support, resilience, fallback and continuity arrangements adequate? | Operational readiness evidence. |  | Yes | Operations / Technology |  |  | Pending
AP29 | Production Readiness | Is there a controlled pilot or phased deployment plan appropriate to risk? | Pilot / rollout plan. |  | No | Project Manager |  |  | Pending
AP30 | Final Approval | Are all mandatory conditions closed or formally accepted by the authorised approval body? | Signed approval / meeting decision. |  | Yes | Approval Body |  |  | Pending
APPROVAL SUMMARY |  |  | APPROVAL RECORD
Checklist Completion | 0% |  | Decision | [Enter] | Approved By | [Enter]
Mandatory Blocks | 0 |  | Approval Date | [Enter] | Next Review | [Enter]
Conditions / Partial Items | 0 |  | Conditions Owner | [Enter] | Target Closure | [Enter]
Passed Items | 0 |  | Evidence Location | [Enter]
Indicative Decision | PENDING COMPLETION
Decision Rationale / Conditions | [Enter rationale / conditions]

## Approval Summary
AI PROJECT APPROVAL — EXECUTIVE SUMMARY
Approval KPI | Value
Completion | 0%
Mandatory Blocks | 0
Conditions | 0
Passed Checks | 0
Indicative Decision | PENDING COMPLETION

## Guidance
AI PROJECT APPROVAL CHECKLIST — EXECUTIVE GUIDANCE
Purpose | Provide a formal governance gate before an AI initiative proceeds to pilot or production.
How to use | Complete the checklist with evidence, owners and conditions. Mandatory items marked No create a blocking condition.
Approval logic | Mandatory checks should pass or be formally resolved before approval. Partial responses create approval conditions.
Risk linkage | The project should be in the AI Use-Case Register and classified using the Risk Classification Matrix. High/Critical cases should have a detailed AI Risk Assessment.
Vendor linkage | For material external suppliers, complete the AI Vendor Assessment and carry unresolved conditions into this approval record.
Agentic AI | AI that takes actions requires explicit permission boundaries, operating limits, human approval where appropriate, monitoring and a tested stop/disable mechanism.
Evidence | Record test results, security/privacy reviews, vendor evidence, policies and risk decisions so approval is auditable.
Re-approval | Material changes to model, vendor, data, permissions, autonomy, business purpose or regulation should trigger reassessment.
Executive principle | Approval is a business decision that expected value justifies residual risk and that accountability and controls are clear.

## Lists
Response
Yes
Partial
No
N/A