## AI Use-Case Register
Use-Case ID | Use-Case Name | Business Function | Business Owner | Executive Sponsor | Problem / Opportunity | Proposed AI Solution | AI Type | Expected Business Benefit | Primary KPI / Success Measure | Estimated Annual Benefit | Estimated Annual Cost | Expected ROI % | Status | Decision | Priority | Risk Rating | Data Sensitivity | Human Oversight | Customer / Employee Impact | Key Risks / Constraints | Controls / Guardrails | Third-Party / Vendor | Target Pilot Date | Target Production Date | Last Review Date | Next Review Date | Evidence / Notes
AI-001 | Submission Data Extraction | Underwriting | Head of Underwriting | CUO | Underwriters spend significant time extracting information from broker submissions. | Extract and structure submission data and flag missing information. | NLP / Document AI | Reduce handling time and improve data consistency. | Average submission handling time | 250000 | 90000 | 177.8% | Pilot | Proceed | High | Moderate | Confidential | Human review | Underwriters and brokers | Incorrect extraction; missing context; data leakage | Confidence thresholds; human review; restricted data access | TBC | 2026-09-15 | 2026-12-01 | 2026-08-15 | 2026-09-15 | Pilot scope limited to lower-complexity submissions.
AI-002 | Executive Knowledge Assistant | Operations | COO | CEO | Senior managers spend time locating policies, reports and internal guidance. | Enterprise retrieval assistant over approved internal knowledge. | Generative AI | Faster access to trusted information and reduced search time. | Average time to locate information | 120000 | 45000 | 166.7% | Assessment | Assess | Medium | Low | Internal | Advisory only | Employees | Hallucination; outdated source material | Approved sources only; citations required; no autonomous actions | TBC | 2026-10-01 | 2027-01-15 | 2026-08-12 | 2026-09-12 | Business case under validation.

## Dashboard
AI USE-CASE GOVERNANCE DASHBOARD
Portfolio KPI | Value | Lifecycle Status | Count | Risk Rating | Count
Registered Use Cases | 2 | Idea | 0 | Low | 1
In Production | 0 | Assessment | 1 | Moderate | 1
High / Very High Risk | 0 | Pilot | 1 | High | 0
Total Estimated Annual Benefit | 370000 | Production | 0 | Very High | 0
|  | On Hold | 0

## Guidance
AI USE-CASE REGISTER — EXECUTIVE GUIDANCE
Purpose | Maintain a single governance record of every material AI use case from idea through assessment, pilot, production and retirement.
Why it matters | An organisation cannot govern AI effectively if it does not know where AI is being used, who owns it, what data it uses, what decisions it influences and what risks it creates.
Use-Case ID | Assign a unique identifier so assessments, approvals, incidents and reviews can be traced to the same record.
Business Owner | The accountable business person responsible for the outcome and ongoing use of the AI capability.
Expected Benefit | Describe the measurable business outcome rather than the technical capability.
ROI | Estimated ROI is calculated automatically from annual benefit and annual cost. Treat it as a business-case indicator, not proof of realised value.
Decision | Use Assess / Proceed / Change / Stop at formal governance reviews.
Risk Rating | High and Very High use cases should receive enhanced governance and assurance.
Human Oversight | Record whether humans advise, review, approve, decide, or supervise bounded autonomous activity.
Controls / Guardrails | Record access restrictions, data limits, approval thresholds, monitoring, logging, escalation, testing and prohibited actions.
Review Cycle | Every production use case should have a named review date, with earlier review after material changes.

## Lists
Status | Risk Rating | Decision | Business Function | AI Type | Data Sensitivity | Human Oversight | Priority
Idea | Low | Assess | Underwriting | Generative AI | Public | Advisory only | Low
Assessment | Moderate | Proceed | Claims | Predictive ML | Internal | Human review | Medium
Pilot | High | Change | Finance | Agentic AI | Confidential | Human approval | High
Production | Very High | Stop | Operations | NLP / Document AI | Personal Data | Human decision | Critical
On Hold |  |  | Customer Service | Computer Vision | Special Category / Highly Sensitive | Human-in-the-loop
Retired |  |  | Sales & Marketing | Other |  | Autonomous within limits
HR
IT / Cybersecurity
Legal / Compliance
Other