## Executive Board Brief
QUARTERLY AI BOARD PACK
Quarterly executive view of AI strategy, portfolio, value, risk, people, regulation, investment and decisions.
Quarter | AI Strategic Position | Portfolio Status | Value Position | Risk Position | Workforce | Regulatory | Investment | Overall RAG | Key Development | Top Opportunity | Top Risk | Management Recommendation | Board Focus
Q3 2026 | AI moving from experimentation toward controlled scaling. | 3 SCALE / 3 PROVE / 1 HOLD / 1 STOP | Positive forecast value; benefit evidence still maturing. | One Critical autonomous-AI control issue remains held. | Readiness improving; change capacity is weakest area. | Core obligations mapped; evidence gaps remain. | Within total budget; funding discipline required. | AMBER | Agentic AI increases both opportunity and control requirements. | Scale proven decision-support and productivity use cases. | Autonomous actions without fully evidenced boundaries and intervention. | Scale selectively; hold autonomous use until controls pass assurance. | Approve priority decisions and challenge evidence behind value and controls.
QUARTERLY SCORECARD
Measure | Current | Target | Trend | RAG | Board Interpretation |  | Measure | Current | Target | Trend | RAG | Board Interpretation
Material AI Use Cases | 8 | 10 | ↑ | GREEN | Portfolio is becoming more focused. |  | Portfolio ROI | 224.6% | 100%+ | ↑ | GREEN | Forecast value remains attractive.
High/Critical Residual Risks | 3 | 0 | → | RED | Material risk requires continued Board visibility. |  | Training Completion | 68.62% | 90% | ↑ | AMBER | Training progressing; role adoption must follow.
Open Board Decisions | 5 | 0 | → | AMBER | Several decisions required this quarter. |  | Compliance Evidence Complete | 37.5% | 90% | ↑ | AMBER | Evidence needs to catch up with framework maturity.
Overdue Actions | 0 | 0 | ↓ | AMBER | Management should close or re-escalate missed actions. |  | Forecast Budget Variance | 40000 | 0 | → | GREEN | Portfolio remains within approved envelope.
BOARD DECISIONS THIS QUARTER
ID | Decision | Recommendation | Priority | Financial Exposure | Risk Impact | Decision Needed | Owner | Timing | Conditions | Status | RAG | Evidence | Board Notes
BD-001 | Autonomous policy servicing agent | Continue HOLD | Critical | 175000 | Critical | Confirm no production deployment until controls evidenced | COO / CISO | This meeting | Independent testing of permissions, monitoring and stop controls | Required | RED | Risk & Governance tab
BD-002 | Underwriting decision support | Continue PROVE | High | 145000 | High | Approve time-bounded extension | CUO | This meeting | Validation, fairness and transparency thresholds | Required | AMBER | Portfolio / Risk tabs
BD-003 | Low-adoption legacy pilot | STOP | Medium | 45000 | Moderate | Approve closure | COO | This meeting | Terminate recurring spend; capture lessons | Required | AMBER | Value / Investment tabs
BD-004 | Workforce implementation capacity | Reprioritise capacity | High |  | Value delivery | Approve protected workflow redesign capacity | COO / CHRO | This meeting | Quarterly adoption/value reporting | Required | AMBER | Workforce tab

## Decisions Required
BOARD DECISIONS REQUIRED
Decision paper summary: what management is asking directors to approve, challenge, hold or stop.
ID | Matter | Type | Recommendation | Priority | Financial Exposure | Risk / Governance | Alternatives | Decision Required | Owner | Target / Review | Conditions | Status | RAG
BD-001 | Autonomous policy servicing agent | Risk / use-case gate | HOLD | Critical | 175000 | Critical residual risk | Proceed / Hold / Stop | Confirm HOLD | COO / CISO | 2026-09-30 | No production access until control evidence passes independent assurance | Decision Required | RED
BD-002 | Underwriting decision support | Use-case gate | PROVE | High | 145000 | High inherent; controlled by human final decision | Scale / Prove / Hold / Stop | Approve defined pilot extension | CUO | 2026-09-20 | Return with validation and transparency evidence | Decision Required | AMBER
BD-003 | Legacy low-adoption pilot | Investment | STOP | Medium | 45000 | Low strategic risk; weak economics | Continue / Redesign / Stop | Approve closure | COO | 2026-09-05 | Close recurring cost | Decision Required | AMBER
BD-004 | AI workforce capacity | Strategic direction | Reprioritise | High |  | Value realisation risk | Maintain / Reprioritise / Add | Approve protected implementation capacity | COO / CHRO | 2026-10-31 | Report adoption and redesigned workflows | Decision Required | AMBER
BD-005 | Regulatory assurance gaps | Governance | Remediate | High |  | Material compliance evidence gaps | Accept / Accelerate / Restrict | Endorse deadlines and escalation | CRO / CISO | 2026-09-30 | Critical missed deadlines return to Board | Decision Required | AMBER

## AI Portfolio
AI PORTFOLIO
Quarterly portfolio of material AI initiatives and management's Scale / Prove / Hold / Stop recommendation.
ID | Initiative | Business Area | Stage | Decision | Executive Owner | Risk | Adoption % | Annual Benefit | Forecast Cost | Net Benefit | ROI | Next Gate
AI-001 | Customer service knowledge assistant | Operations | Production | SCALE | COO | Moderate | 78% | 180000 | 65000 | 115000 | 176.9% | Quarterly benefit review
AI-002 | Underwriting decision support | Underwriting | Pilot | PROVE | CUO | High | 52% | 320000 | 145000 | 175000 | 120.7% | Validation / scale decision
AI-003 | Claims document triage | Claims | Production | SCALE | Claims Director | Moderate | 72% | 240000 | 90000 | 150000 | 166.7% | Quarterly monitoring
AI-004 | Internal drafting assistant | Corporate Services | Production | SCALE | COO | Low | 69% | 75000 | 30000 | 45000 | 150% | Adoption review
AI-005 | Autonomous policy servicing agent | Operations | Assessment | HOLD | COO / CISO | Critical | 10% | 400000 | 175000 | 225000 | 128.6% | Control assurance
AI-006 | Management insight assistant | Finance | Pilot | PROVE | CFO | Moderate | 48% | 120000 | 55000 | 65000 | 118.2% | Benefit proof
AI-007 | Marketing content generator | Marketing | Pilot | PROVE | CMO | Moderate | 61% | 60000 | 25000 | 35000 | 140% | Quality / adoption review
AI-008 | Legacy low-adoption AI pilot | Operations | Pilot | STOP | COO | Moderate | 18% | 20000 | 45000 | -25000 | -55.56% | Closure
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Business Value
AI BUSINESS VALUE
Quarterly view of expected and realised AI value, adoption and benefit confidence.
ID | Initiative | Benefit Type | Benefit Baseline | Realised YTD | Annual Forecast Cost | Annual Forecast Benefit | Net Benefit | Benefit Confidence | RAG
AI-001 | Customer service knowledge assistant | Productivity / service | Hours saved + service quality | 90000 | 65000 | 180000 | 115000 | High | GREEN
AI-002 | Underwriting decision support | Decision quality / productivity | Cycle time + underwriting insight | 65000 | 145000 | 320000 | 175000 | Medium | AMBER
AI-003 | Claims document triage | Productivity | Handling time | 110000 | 90000 | 240000 | 150000 | High | GREEN
AI-004 | Internal drafting assistant | Productivity | Drafting time | 32000 | 30000 | 75000 | 45000 | Medium | GREEN
AI-005 | Autonomous policy servicing agent | Efficiency / service | Automation rate | 0 | 175000 | 400000 | 225000 | Low | RED
AI-006 | Management insight assistant | Decision support | Reporting effort | 28000 | 55000 | 120000 | 65000 | Medium | AMBER
AI-007 | Marketing content generator | Productivity | Content production time | 20000 | 25000 | 60000 | 35000 | Medium | AMBER
AI-008 | Legacy low-adoption AI pilot | Productivity | Usage / time saving | 5000 | 45000 | 20000 | -25000 | Low | RED
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Risk & Governance
AI RISK & GOVERNANCE
Quarterly view of material residual risks, control effectiveness, incidents and governance actions.
Risk ID | AI / Scope | Risk Theme | Inherent Risk | Key Controls | Control Effectiveness | Residual Risk | Risk Appetite | Owner | Action | Target | RAG
R-001 | AI-005 | Agent authority / cyber | Critical | Least privilege; action limits; monitoring; stop control | Partial | Critical | Outside | CISO / COO | Complete independent control testing | 2026-08-31 | RED
R-002 | AI-002 | Decision quality / fairness | High | Human final decision; validation; monitoring | Partial | High | Within with conditions | CUO / CRO | Complete validation evidence | 2026-09-20 | AMBER
R-003 | Enterprise | Sensitive data exposure | High | Approved tools; access control; data rules; DLP | Effective | Moderate | Within | CISO / DPO | Continue monitoring | 2026-09-30 | GREEN
R-004 | Enterprise | Third-party AI dependency | High | Vendor assessment; contracts; monitoring; exit planning | Partial | High | Within with conditions | CTO / Procurement | Close assurance condition | 2026-10-10 | AMBER
R-005 | Enterprise | Shadow / unapproved AI | High | Acceptable use policy; approved tool catalogue; awareness | Partial | Moderate | Within | CHRO / CISO | Improve detection and reinforcement | 2026-10-31 | AMBER
R-006 | Enterprise | AI incident readiness | High | Incident procedure; escalation; logging | Effective | Moderate | Within | CISO / CRO | Run tabletop exercise | 2026-11-14 | GREEN
R-007 | Enterprise | Weak human accountability | High | Named owners; approval gates; RACI | Effective | Low | Within | AI Sponsor | Quarterly ownership review | 2026-09-30 | GREEN

## Workforce Readiness
AI WORKFORCE READINESS
Quarterly readiness across leadership, skills, adoption, responsible use and change capacity.
Capability | Current Maturity | Target | Training Target | Training Complete | Active Adoption | Gap | Management Action | RAG
Leadership | 3 | 4 | 20 | 13 | 55% | Practical executive confidence | Complete scenario-based leadership programme | AMBER
Role-based Skills | 3 | 4 | 260 | 145 | 52% | Priority users not yet fully competent | Align training to live use cases | AMBER
Responsible Use | 4 | 5 | 850 | 697 | 75% | Uneven reinforcement | Scenario training + manager reinforcement | AMBER
Change Capacity | 2 | 4 | 95 | 38 | 40% | Insufficient workflow redesign capacity | Protect implementation time | RED
Data / AI Literacy | 3 | 4 | 850 | 527 | 57% | Core literacy still developing | Continue targeted learning | AMBER
Specialist Capability | 3 | 4 | 35 | 27 | 65% | Scaling needs more assurance/security depth | Build specialist capability | AMBER
AI Champions | 3 | 4 | 60 | 42 | 68% | Coverage uneven by function | Expand champion network | GREEN

## Regulatory
AI REGULATORY & GOVERNANCE
Quarterly view of material obligations, evidence status and regulatory change.
Obligation / Theme | Scope | Mapping | Compliance Status | Gap Severity | Evidence Status | Owner | RAG
Privacy & data governance | Enterprise | Mapped | Compliant | None | Complete | DPO | GREEN
Transparency / explainability | AI-002 | Mapped | Partial | High | Partial | CUO / Compliance | AMBER
Human oversight | AI-005 | Mapped | Gap | Critical | Partial | COO / Compliance | RED
Cybersecurity / permissions | AI-005 | Mapped | Gap | Critical | Partial | CISO | RED
Vendor governance | Enterprise | Mapped | Partial | High | Partial | Procurement / CISO | AMBER
Incident management | Enterprise | Mapped | Compliant | None | Complete | CISO / CRO | GREEN
Use-case approval | Enterprise | Mapped | Compliant | None | Complete | AI Governance Lead | GREEN
Monitoring / change control | Enterprise | Mapped | Partial | High | Partial | AI Governance Lead | AMBER

## Investment & Budget
AI INVESTMENT & BUDGET
Quarterly view of approved budget, forecast spend and expected value by initiative.
ID | Initiative | Decision | Cost Category | Approved Budget | Forecast Spend | Variance | Annual Benefit | Funding Status | RAG
AI-001 | Customer service knowledge assistant | SCALE | Technology / Licences | 70000 | 65000 | 5000 | 180000 | On Track | GREEN
AI-002 | Underwriting decision support | PROVE | Implementation / Integration | 150000 | 145000 | 5000 | 320000 | On Track | AMBER
AI-003 | Claims document triage | SCALE | Technology / Licences | 95000 | 90000 | 5000 | 240000 | On Track | GREEN
AI-004 | Internal drafting assistant | SCALE | People / Training | 35000 | 30000 | 5000 | 75000 | On Track | GREEN
AI-005 | Autonomous policy servicing agent | HOLD | Implementation / Integration | 180000 | 175000 | 5000 | 400000 | At Risk | RED
AI-006 | Management insight assistant | PROVE | Technology / Licences | 60000 | 55000 | 5000 | 120000 | On Track | AMBER
AI-007 | Marketing content generator | PROVE | People / Training | 30000 | 25000 | 5000 | 60000 | On Track | AMBER
AI-008 | Legacy low-adoption AI pilot | STOP | Governance / Assurance | 50000 | 45000 | 5000 | 20000 | Close | AMBER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Board Questions
BOARD AI QUESTIONS CHECKLIST
Questions directors should use to challenge the quarterly AI Board Pack.
Theme | Board Question | Response | Concern | Evidence / Commentary | Follow-Up | RAG
Strategy | Do we have a clear AI strategy linked to measurable business priorities? | Partially | Medium | Roadmap is being embedded. | Yes | AMBER
Business Value | Can management demonstrate measurable value from AI investment? | Partially | High | Some benefit evidence remains forecast rather than realised. | Yes | AMBER
Investment | Are we prepared to stop funding initiatives that do not prove value? | Yes | Medium | STOP decision proposed for low-adoption pilot. | No | GREEN
Risk | Is any material AI exposure outside approved risk appetite? | Yes | Critical | AI-005 remains held. | Yes | RED
Governance | Can management evidence that controls operate in practice? | Partially | High | Assurance evidence incomplete in several areas. | Yes | AMBER
Regulation | Can management demonstrate applicable obligations and compliance evidence? | Partially | High | Critical gaps linked to autonomous use case. | Yes | AMBER
People | Are we redesigning workflows rather than simply deploying AI tools? | Partially | High | Change capacity is the weakest readiness area. | Yes | AMBER
Data & Security | Are permissions and credentials limited to what AI genuinely needs? | Partially | Critical | Further agentic-AI testing required. | Yes | RED
Vendors | Do we have sufficient assurance, resilience and exit arrangements? | Partially | High | One material vendor assurance gap remains. | Yes | AMBER
Agentic AI | Can we constrain, monitor, interrupt and stop autonomous AI? | No | Critical | Controls not yet fully evidenced. | Yes | RED
Accountability | Is a named executive accountable for every material AI use case? | Yes | Low | Ownership recorded across portfolio. | No | GREEN

## Actions & Decisions
QUARTERLY ACTIONS & DECISIONS LOG
Track Board decisions, conditions, actions, owners, evidence and re-escalation.
Action ID | Decision / Source | Action / Condition | Owner | Date Raised | Target Date | Status | Evidence / Output | Overdue? | Next Escalation
ACT-001 | BD-001 | Complete independent testing of agent authority boundaries and stop controls. | CISO | 2026-08-19 | 2026-08-31 | In Progress | Test and assurance pack |  | Board / Risk Committee
ACT-002 | BD-002 | Complete validation, fairness and transparency evidence. | CUO | 2026-08-19 | 2026-09-20 | In Progress | Validation pack |  | AI Governance Forum
ACT-003 | BD-003 | Terminate recurring legacy pilot expenditure. | COO | 2026-08-19 | 2026-09-05 | Open | Closure confirmation |  | CFO
ACT-004 | BD-004 | Allocate protected workflow redesign capacity. | COO / CHRO | 2026-08-19 | 2026-09-15 | Open | Resource plan |  | CEO
ACT-005 | BD-005 | Close Critical regulatory/governance evidence gaps. | CRO / CISO | 2026-08-19 | 2026-09-30 | In Progress | Remediation evidence |  | Board / Risk Committee
ACT-006 | Risk R-006 | Run AI incident tabletop exercise. | CISO / CRO | 2026-08-19 | 2026-11-14 | Open | Exercise record |  | Executive AI Forum
ACT-007 | Workforce | Expand role-based AI champion coverage. | CHRO / COO | 2026-08-19 | 2026-10-31 | Open | Champion coverage report |  | Executive AI Forum
Formulas:
Overdue? = IF(AND([Target Date]<>"",[Target Date]<TODAY(),[Status]<>"Complete",[Status]<>"Closed"),"YES","")

## Pack Instructions
QUARTERLY AI BOARD PACK — INSTRUCTIONS
How management should prepare and use this pack each quarter.
Section | Guidance
Executive Board Brief | Complete last. Summarise material movement since the previous quarter, the overall RAG, top opportunity, top risk and the decisions directors are being asked to make.
Decisions Required | Include only material matters requiring Board approval, challenge, risk acceptance, strategic direction or funding. State management's recommendation first.
AI Portfolio | Include material use cases only. Apply Scale / Prove / Hold / Stop consistently and record the next decision gate.
Business Value | Report realised benefits separately from forecasts. Keep baselines stable unless there is a documented reason to reset them.
Risk & Governance | Focus on residual risk and operating effectiveness of controls. Escalate exposure outside appetite and serious incidents promptly.
Workforce Readiness | Measure practical adoption and role readiness, not training attendance alone. Highlight where change capacity is limiting value.
Regulatory | Maintain an owned obligations register outside the pack; bring material changes, gaps and evidence issues into the quarterly view.
Investment & Budget | Show full AI cost—not just licences—including integration, people, governance and assurance. Link funding to portfolio decisions.
Board Questions | Use this as the directors' challenge checklist. Responses should be evidence-based rather than simple management assertions.
Actions & Decisions | Carry forward open Board conditions and actions until closure. Missed material conditions should be re-escalated.
Suggested Cadence | Prepare quarterly for the Board or relevant committee. Management dashboards and action registers should normally be maintained monthly.
Quarterly Narrative | Directors should be able to understand in a few minutes: what changed, what value is being created, what could go wrong, whether controls work, and what they need to decide.
Use with Toolkit | The detailed Governance Toolkit, dashboards, assessments and registers should provide the evidence behind this concise Board pack.